## Sheet1
Group | B6
Team Members | Carlos Araiza | Oskar Garcia | Angel Lugo | Sebastian Lizalde
Project name | Automated Irrigation System
Due date
Start of the development of the project | 2026-04-23
Project presentation and final delivery | 2026-06-03
Week Number | Week 1 - Week 2 | Week 3 - Week 4 | Week 5 - Week 6 | Week 7
Week Date | 4/22/2026 - 5/6/2026 | 5/6/2026 - 5/20/2026 | 5/20/2026 - 6/3/2026 | 2026-06-03
Project Activities Descriptions with ownership of activities | Bi-weekly deliverables
Project Schedule Plan - Everyone | Spreadsheeet with the activities ordered by dates.
Definition of the budget and materials list plan - Everyone | Spreadsheeet with the materials needed and the cost of each.
Investigation about the operation of the hardware to be used - Carlos Araiza & Angel Lugo | Document with information about how each component works.
Research of the peripherals and pins that will be used in the STM32 - Oskar García & Sebastian Lizalde | Document indicating the peripherals and pins that will work as I/O .
First draft of the automation system design - Carlos Araiza & Sebastian Lizalde | SolidWorks Design.
STM32 Nucleo-64 environment setup and GPIO configuration - Sebastian Lizalde & Oskar García | GPIO driver with the source code and header file.
Soil mosture, temperature, and water level sensor integration in the STM32 - Carlos Araiza & Angel Lugo | Document with the explanation of how the sensors will work as inputs into the STM32.
Implementation of the valve control, water pumps and relay module in the STM32 - Sebastian Lizalde & Angel Lugo | Document that will explain how the actuators respond as outputs of the STM32.
LCD & push-button integration in the STM32 - Carlos Araiza & Oskar García | Document that explains how the I2C will be applied through the display and buttons
Designing of the code that will make the hardware work with the STM32 - Sebastian Lizalde & Oskar García | Document code development and explain how it works with the STM32 and all the components.
Design and control of each section - Carlos Araiza & Sebastian Lizalde | SolidWorks design along with code modifications to control each section of the system.
Section priority control via sensor testing - Angel Lugo & Oskar García | Code testing of sensor components in each section.
Section priority control via manual testing - Sebastian Lizalde & Angel Lugo | Testing of LCD and push-botton integration for each section.
User interface development - Carlos Araiza & Oskar García | Develop and provide documentation on how the irrigation system is controlled.
System integration and closed-loop testing - Sebastian Lizalde & Oskar García | Provide code corrections, and changes in design if needed before final assembly.
Prototype assembly and final code debugging - Angel Lugo & Carlos Araiza | Fully assembled prototype with debugged code ready for final validation
Final project documentation - Everyone | Complete project report including design, firmware, testing and results.
Presentation preparation - Everyone | Presentation slides and live demo script.
Final project review and corrections - Everyone | Revised and corrected final project report.
Final system validation - Everyone | Final validation report confirming all system requirements are met.
Final project delivery and presentation - Everyone | Delivered final project and presentation to professor.